## Sheet1
Task | Status | Last Worked On | Notes
Exhaust System | Waiting on parts |  | The exhaust system in in father-in-law's garage
Tires | Waiting on parts |  | Need to decide about getting 14 inch tires, or replace wheels right away
Fuel tank | Sitting |  | Need to verify I have all the parts for the sending unit and all fuel lines
Seats | Sitting |  | Need to verify I have the new covers and install them
Carpet | Sitting |  | Need to verify I have the replacement carpet
Tail lights | Sitting |  | Need to install
Paint | waiting |  | Need to pick color, save money and get it painted
Bumpers | Waiting on parts |  | Sitting in father-in-law's garage
Engine | need to research |  | Engine has been sitting for several years after rebuild, how long is assembly lube good for?
Transmission | need to research |  | Transmission has been sitting for several years after rebuild, does it need anything before starting car?
Shift linkage | Need parts |  | A piece of the transmission linkage broke, do I replace it, or just look at upgrading the transmission right away?